Local Control Accountability Plan

Sample Timeline for 2015-2016

| Month/Quarter | Action | Notes and Best Practices |
| --- | --- | --- |
| September - November | Assess and Engage |  |
| September 2014 | - Establish LCAP development process, team, timeline | Resources: http://lcff.wested.org/making-a-plan-to-develop-the-lcap/ |
| October 2014 | - Gather data for analysis and evaluate progress - Determine Relevant Stakeholder groups | Determine which metrics will be used to provide useful information to measure actions/expenses and communicate with stakeholders. Best Practice - Ensure that EL, FY, and LI parents are adequately represented. |
| November | Stakeholder Engagement/Input: - Students - Teachers - Principals - Parents - Bargaining Units - School Personnel | Consider methods to get meaningful input from stakeholders. Best Practice – Establish an LCAP committee composed of relevant stakeholders that will be together for a couple of years and engage them at a deep level. |
| December - February | Draft and Consult |  |
| December 2014 | - Compile input received from stakeholders and analyze for trends, needs, and priorities - Update needs assessment based on 13-14 data and new stakeholder input | Best Practice - A robust needs assessment is the foundation of an effective LCAP. Best Practice – Define “base or core” program for district. |
| January 2015 | - Governor’s Proposed Budget - Meet with District LCAP Team - Identify goals, actions, services and align resources to Governor’s Budget - Provide Board with LCAP Update | Prioritize draft goals and actions to be added for the next year. Determine any changes or revisions to existing plan. Maintain transparency, share input from stakeholders and data with Board. |
| February 2015 | - Consult with bargaining units | Provide union with notice that this is their official consultation. |
| March-April | Share and Respond |  |
| March 2015 | - Finalize Draft of LCAP – Inform stakeholders |  |
|  | - Provide Board with LCAP Update | Share Draft LCAP. Clarify Board direction and goals. |
|  | - DELAC and Parent Advisory Committee reviews and comments on LCAP - Superintendent must respond in writing to their input | Regulation is specific on need to engage EL parents in process and have them review LCAP if 15% or 50 students are EL. |
| April 2015 | - Complete Annual Progress section using local data, assessments, or other metrics as defined in plan | Best Practice – Having clearly defined state and local metrics for each goal facilitates this section. |
|  | - Consult with COE for technical assistance on LCAP documentation and content |  |
|  | - Establish system to gather public input on completed LCAP | Consider available online resources. |
|  | - Board Presentation on LCAP - Final review prior to public hearing |  |
| May-June | Decide and Adopt |  |
| May 2015 | State Budget Revision | Determine changes, if any, to proposed LCAP. May require prioritizing or delaying specific actions. |
|  | Public Hearing at a board meeting - LCAP - Budget |  |
|  | - Provide for public comment period - Provide notice to stakeholders of opportunity to submit written comment | Best Practice – Create an executive summary to share with stakeholders. Include overview of the LCAP and Budget. |
|  | - Consult with COE as needed to ensure compliance |  |
| June 2015 | - Board Meeting – Adoption of LCAP and Budget | Adoption of LCAP needs to occur prior to July 1st. |
| 5 days after adoption | - Send LCAP to SLOCOE for Approval |  |

Final Thoughts/Suggestions:

- The first year, 2014-2015, is a year of implementation.  Now it’s time to execute.

- Remember that the life cycle of the LCAP is one of continuous reflection, adaptation, and growth – now is the time to reflect on what worked well and what needs to be improved.

- Establish a plan/process for annually updating the LCAP.

- Your local needs assessment will be the foundation of the LCAP.

- Have a purpose for all stakeholder meetings.    Make the data accessible and focused.

- Maintain transparency and engage a wide spectrum of your community.

- Collaboration with employee groups is more important than ever but increasingly difficult.

- Systemic change will require courage and strong leadership on both sides of the bargaining table.